## Risk Register
ID | Risk Description | Pre-L (1–5) | Pre-C (1–5) | Pre-Score (L×C) | Pre-Severity | Mitigation (preventive) | Contingency (reactive) | Post-L (1–5) | Post-C (1–5) | Post-Score (L×C) | Post-Severity
TR-01 | Capture mechanism fails to secure tumbling target (1 rpm about arbitrary axis) | 4 | 5 | 20 | Critical | Design capture mechanism with wide compliance (tolerant to ≥2 rpm, multi-axis tumble); perform Light Detection and Ranging (LIDAR) based motion characterisation prior to grappling. | Abort capture sequence and retreat to safe hold point (>50 m); re-characterise target tumble; attempt secondary capture with adjusted alternative grappling settings; if repeated failure, mark target as non-recoverable and proceed to next. | 2 | 5 | 10 | High
TR-02 | Debris generation during disassembly (fragments > 1 cm released into GEO belt) - Recycling Hub | 3 | 5 | 15 | High | Use low-energy cutting tools within an enclosed capture cage to contain any loose pieces; design and test the disassembly process to minimise fragment release. | Stop disassembly immediately on debris detection; deploy debris-containment net (capture fragments); use onboard cameras to track fragments. | 2 | 4 | 8 | Medium
TR-03 | Autonomous Failure Management (AFM) failure during close-proximity operations (range < 100 m) leads to a collision with the target | 3 | 5 | 15 | High | Implement triple-redundant AFM with independent sensor chains (LIDAR, camera); extensive simulation of failure modes. | Trigger autonomous collision-avoidance manoeuvre (CAM) to retreat to safe distance; switch to backup AFM; resume only after ground confirmation; if both backups fail, abort to manoeuvre. | 2 | 5 | 10 | High
TR-04 | Propellant depletion before completion of all 5 capture missions | 3 | 4 | 12 | High | Conservative ΔV budget with ≥20 % margin; optimised mission sequencing to minimise transfers; high-Isp electric propulsion for orbit raising. | Reprioritise remaining captures based on value/proximity; skip lowest-priority target(s). | 2 | 4 | 8 | Medium
TR-05 | Navigation sensor failure during final approach (range < 10 m) causes position error exceeding 1 m | 3 | 4 | 12 | High | Redundant navigation architecture (LIDAR + stereo cameras + flash imager) with cross-checking; calibrate sensors pre-approach; define abort triggers on position error >0.3 m. | Hold position and switch to backup sensor chain; if error persists, retreat to 100 m, recalibrate, and re-approach; escalate to ground for teleoperated final approach if available. | 2 | 4 | 8 | Medium
TR-06 | Thermal control failure causes electronics or propellants to exceed operational temperature range | 2 | 4 | 8 | Medium | Active thermal control with redundant heaters/radiators; Multi-Layer Insulation (MLI) on critical components; thermal model validated by Thermal Vacuum (TVAC) testing; temperature margins ≥10 °C against operational limits. | Enter thermal safe mode: reorient spacecraft to balance solar input, dispose of non-critical loads, activate survival heaters; resume operations after temperatures stabilise within limits. | 1 | 4 | 4 | Low
TR-07 | Propulsion failure during critical phase: Loss of the main propulsion system during approach. | 2 | 5 | 10 | High | Dual-propulsion (main) system with isolatable branches; pre-burn tests; conservative duty cycles; redundant thrusters. | Switch to backup propulsion system; if unavailable, use (Reaction Control System) RCS for safe retreat manoeuvre; place spacecraft in stable hold orbit and assess recovery options from ground. | 1 | 5 | 5 | Medium
TR-08 | EOL spacecraft remains in GEO protected zone (35,586–35,986 km) after mission end instead of being transferred to the Recycling Hub | 2 | 5 | 10 | High | Reserve dedicated end-of-life ΔV to transfer the spacecraft to the Recycling Hub at mission end; maintain hub rendezvous capability throughout mission life. | If primary EOL transfer burn fails, execute transfer using residual Reaction Control System (RCS) propellant in multiple smaller burns; if still unable to reach the hub, raise orbit to graveyard zone (≥300 km above GEO) and notify regulators. | 1 | 5 | 5 | Medium
TR-09 | Micrometeoroid or orbital debris impact penetrates propulsion in GEO graveyard environment | 2 | 4 | 8 | Medium | Shielding (MLI) over propellant tanks; redundant tank isolation valves; orbit selection minimising debris exposure; periodic leak detection via pressure sensors. | Isolate affected propellant branch via valves; switch to redundant tank; reduce remaining mission scope to match available propellant; escalate to graveyard disposal if leak uncontained. | 1 | 4 | 4 | Low
TR-10 | Communication blackout during a critical autonomous sequence causes loss of ground override capability | 3 | 3 | 9 | Medium | Pre-loaded autonomous safe-state behaviour for any comm loss >X minutes; redundant Telemetry, Tracking & Command (TT&C) systems (S-band + backup); use of multiple ground stations and relay satellites during critical ops. | Spacecraft autonomously enters safe hold and aborts active sequence; ground re-establishes link via secondary station/antenna; resume operations only after full check and state verification. | 2 | 3 | 6 | Medium
TR-11 | Solar panel damage during contact with tumbling target reduces power by > 50% | 3 | 4 | 12 | High | Foldable solar arrays retracted during contact phases; protective shielding over cells facing target; capture geometry analysis to keep arrays clear of contact zones. | Reconfigure power management: dispose of non-essential loads, throttle electric propulsion, prioritise survival systems; reorient remaining array area for max insolation (amount of sunlight hitting the solar panels); adjust mission scope to match available power. | 2 | 4 | 8 | Medium
TR-12 | Target spacecraft misidentified prior to capture, causing a failed grapple or structural overload | 3 | 4 | 12 | High | Pre-mission target catalogue verification using ground radar/optical and onboard imagery; ID confirmation via multiple features (shape, radio signal) before committing to capture; ground approval required. | Abort capture before mechanical contact; retreat to safe distance (>100 m); re-image and re-identify target; if confirmed wrong, abandon engagement and proceed to next valid target. | 2 | 4 | 8 | Medium
TR-13 | Low Technology Readiness Level (TRL) of critical enabling technologies (capture mechanism, disassembly tool) at mission development start | 4 | 4 | 16 | High | Early technology readiness raising programme with Engineering Model (EM) and Qualification Model (QM) milestones; parallel technology paths for highest-risk items (capture, disassembly); ESA funding to mature technology to TRL 6 (SEAD guideline) before Preliminary Design Review (PDR). | Trigger fallback technology selected at PDR; alter mission objectives (e.g., capture only, no disassembly) to match achieved TRL; alter schedule and budget with sponsor accordingly. | 2 | 4 | 8 | Medium
TR-14 | Collision with an active GEO spacecraft during transfer or Rendezvous and Proximity Operations (RPO) | 2 | 5 | 10 | High | Coordinate trajectory with operators of nearby active GEO spacecraft; collision risk assesement; enforce keep-out zones; CAM capability always armed. | Execute pre-planned collision-avoidance manoeuvre on warning; notify operator and regulators; re-plan rendezvous timeline once safe. | 1 | 5 | 5 | Medium
TR-15 | Total mission cost exceeds the €500 Million boundary due to technology development overruns | 3 | 4 | 12 | High | Cost baseline with ≥20 % margin; monthly budget tracking to compare planned vs actual cost and schedule progress; reconsider options identified in advance and tied to cost triggers. | Re-evaluate scope; seek additional funding from ESA/partners; if unavailable, terminate at next mission step with controlled disposal. | 2 | 4 | 8 | Medium
TR-16 | GEO radiation-induced damage to the onboard computer, causing software corruption | 3 | 4 | 12 | High | Use a radiation-resistant processor and memory; periodic memory backup and refresh; shielded electronics box. | Autonomous reboot to last known good state; switch to redundant computer system; reload software image from protected storage; ground-commanded recovery if autonomous recovery fails. | 2 | 4 | 8 | Medium
TR-17 | Electrostatic discharge (ESD) event due to GEO plasma charging damages electronics or proximity sensors | 2 | 4 | 8 | Medium | Conductive surface coatings and straps to prevent differential charging; ESD-protected circuits on sensors. | Reset affected sensor/electronics; switch to redundant unit; pause proximity ops until charging conditions return (post-eclipse); validate sensor health before resuming approach. | 1 | 4 | 4 | Low
TR-18 | Residual toxic or reactive propellant in target spacecraft creates hazard during disassembly operations | 3 | 4 | 12 | High | Check target propellant state (operator records); planned disassembly sequence to avoid propellant tanks. | Stop disassembly on leak detection; retreat to safe distance (TBD); reassess viability and either resume with revised plan or abandon target. | 2 | 4 | 8 | Medium
TR-19 | ADCS lacks sufficient torque to de-tumble the combined spacecraft+target body within a 30-minute window (can change the time interval just randomish realistic time set) | 3 | 4 | 12 | High | Size ADCS reaction wheels and thrusters with ≥30 % torque margin against worst-case combined inertia; characterise target inertia pre-capture via observed tumble characteristics. | Extend de-tumble window using RCS thrusters in addition to wheels; if still insufficient, release target via controlled separation and reattempt capture after re-planning. | 2 | 4 | 8 | Medium
TR-20 | Star tracker blinding by the Sun, Moon or Earth during an eclipse transition causes loss of attitude knowledge | 3 | 3 | 9 | Medium | Two independent star tracker units; Sun/Earth/Moon exclusion angles in attitude planner; eclipse-aware attitude profile. | Inertial Measurement Unit (IMU) maintains attitude through the blinding interval; on recovery, re-acquire attitude on the second tracker and verify before resuming ops; if attitude knowledge is lost, enter sun-pointing safe-hold and recover from ground. | 2 | 3 | 6 | Medium
TR-21 | Thruster Exhaust Contact: Hot exhaust gases emitted during proximity operations melt or structurally weaken target surfaces, leading to fragmentation or unpredictable attitude dynamics that prevent successful capture. | 2 | 4 | 8 | Medium | Model thruster exhaust to define minimum safe standoff distances; use low-thrust RCS during proximity ops; cold-gas thrusters for final approach where feasible. | Stop thrusting and drift to a safe distance; reassess target integrity via imaging; if surface damage is observed, abandon the target and report fragmentation to regulators. | 1 | 4 | 4 | Low
TR-22 | Timeline extension: Additional approach attempts, or corrections, may significantly extend the overall mission duration and resource use | 2 | 3 | 6 | Medium | Schedule reserve of ≥30 % at mission level; pre-approved replan templates for common anomalies. | Activate descope: reduce number of capture attempts per target or skip lowest-priority target; renegotiate ground resources and operator availability to recover schedule. | 1 | 3 | 3 | Low
TR-23 | On-board storage structure for extracted components fails under repeated GEO thermal cycling (-180 to +150 °C) RANGE OF TEMPREATURES GOD DID | 2 | 4 | 8 | Medium | Storage rack qualified to GEO thermal cycling (-180/+150 °C) over mission life ×1.5 (margin); material selection with matched Coefficient of Thermal Expansion (CTE); periodic structural health monitoring via strain sensors. | Restrain affected stored components via backup tie-down mechanism; replan disposal with reduced storage capacity; if structural integrity compromised, dispose of contents to the recycling hub. | 1 | 4 | 4 | Low
TR-24 | GNC mode transition failure (transfer→RPO→capture→departure) leaves spacecraft in undefined state | 2 | 4 | 8 | Medium | GNC mode-transition logic with state machine verified by model checking; hardware-in-the-loop (HIL) testing of all transition paths, including failures; ground operations checking at each transition. | Spacecraft falls into predefined safe-hold mode on an undefined state; ground analyses telemetry, uploads the recovery sequence, and recommands the transition step-by-step. | 1 | 4 | 4 | Low
TR-25 | Launch vehicle anomaly or delay results in loss of spacecraft or failure to reach target GEO orbit | 1 | 5 | 5 | Medium | Select reliable launcher with proven GEO record; insurance coverage for launch and early ops; secondary launch opportunity identified in case of delay. | Claim insurance and procure replacement launch slot; if spacecraft lost, restart procurement on revised schedule; if delay only, hold spacecraft in storage with periodic checks. | 1 | 5 | 5 | Medium
TR-26 | Unknown or unexpected centre-of-mass offset in captured debris causes uncontrolled attitude divergence of the combined system during transport | 3 | 4 | 12 | High | Estimate target CoM from design data and pre-capture observation; conservative attitude rate limits during transport. | Engage RCS to damp divergence; if uncontrollable, release target into stable disposal orbit and continue mission without it. | 2 | 3 | 6 | Medium
TR-27 | Recycling hub loses station-keeping capability and drifts from its operational position, preventing tug rendezvous and debris handover | 2 | 4 | 8 | Medium | Hub designed with redundant station-keeping propulsion; periodic orbit-determination from ground; reserve propellant margin ≥25 %; collision-avoidance autonomy (Use of CAMs). | Tug holds debris; while ground commands hub recovery using backup thrusters; if hub unrecoverable, tug performs direct graveyard disposal of debris. | 1 | 4 | 4 | Low
TR-28 | Docking mechanism fails during tug return to recycling hub with debris attached, preventing debris handover and blocking subsequent capture cycles | 2 | 4 | 8 | Medium | Redundant docking mechanism with soft-capture and hard-capture stages; extensive on-ground docking qualification; pre-docking alignment via vision system with abort thresholds. | Retry docking up to N attempts with adjusted approach; if persistent failure, tug carries debris directly to graveyard orbit and releases there, ending capture cycle. | 1 | 4 | 4 | Low
TR-29 | Structural fragmentation of target spacecraft during capture due to undetected material fatigue or microcracking, generating secondary debris | 2 | 5 | 10 | High | Pre-capture inspection via high-resolution imaging to detect surface fatigue/cracks; gentle, distributed grasp loads; load monitoring during capture with abort thresholds. | On fragmentation detection, stop capture, retreat with capture cage closed to contain fragments; track and characterise debris; release contained fragments at recycling hub. | 2 | 5 | 10 | High
TR-30 | Ground mission operations centre failure causes extended loss of spacecraft commanding and telemetry monitoring during an active operational phase | 2 | 4 | 8 | Medium | Geographically redundant primary and backup Mission Operations Centre (MOC); rehearsed handover procedures; spacecraft autonomy sized to operate ≥48 h without ground contact. | Spacecraft continues on stored timeline or enters safe-hold past autonomy window; activate backup MOC; resume nominal commanding once link and operations are restored. | 1 | 4 | 4 | Low
| Legend: | Low (1–4) | Medium (5–9) | High (10–16) | Critical (20–25)

## Risk Summary
ID | Risk Description | Pre-L (1–5) | Pre-C (1–5) | Pre-Score (L×C) | Pre-Severity | Post-L (1–5) | Post-C (1–5) | Post-Score (L×C) | Post-Severity
TR-01 | Capture mechanism fails to secure tumbling target (1 rpm about arbitrary axis) | 4 | 5 | 20 | Critical
TR-02 | Debris generation during disassembly (fragments > 1 cm released into GEO belt) - Recycling Hub | 3 | 5 | 15 | High
TR-03 | Autonomous Failure Management (AFM) failure during close-proximity operations (range < 100 m) leads to a collision with the target | 3 | 5 | 15 | High
TR-04 | Propellant depletion before completion of all 5 capture missions | 3 | 4 | 12 | High
TR-05 | Navigation sensor failure during final approach (range < 10 m) causes position error exceeding 1 m | 3 | 4 | 12 | High
TR-06 | Thermal control failure causes electronics or propellants to exceed operational temperature range | 2 | 4 | 8 | Medium
TR-07 | Propulsion failure during critical phase: Loss of the main propulsion system during approach. | 2 | 5 | 10 | High
TR-08 | EOL spacecraft remains in GEO protected zone (35,586–35,986 km) after mission end instead of being transferred to the Recycling Hub | 2 | 5 | 10 | High
TR-09 | Micrometeoroid or orbital debris impact penetrates propulsion in GEO graveyard environment | 2 | 4 | 8 | Medium
TR-10 | Communication blackout during a critical autonomous sequence causes loss of ground override capability | 3 | 3 | 9 | Medium
TR-11 | Solar panel damage during contact with tumbling target reduces power by > 50% | 3 | 4 | 12 | High
TR-12 | Target spacecraft misidentified prior to capture, causing a failed grapple or structural overload | 3 | 4 | 12 | High
TR-13 | Low Technology Readiness Level (TRL) of critical enabling technologies (capture mechanism, disassembly tool) at mission development start | 4 | 4 | 16 | High
TR-14 | Collision with an active GEO spacecraft during transfer or Rendezvous and Proximity Operations (RPO) | 2 | 5 | 10 | High
TR-15 | Total mission cost exceeds the €500 Million boundary due to technology development overruns | 3 | 4 | 12 | High
TR-16 | GEO radiation-induced damage to the onboard computer, causing software corruption | 3 | 4 | 12 | High
TR-17 | Electrostatic discharge (ESD) event due to GEO plasma charging damages electronics or proximity sensors | 2 | 4 | 8 | Medium
TR-18 | Residual toxic or reactive propellant in target spacecraft creates hazard during disassembly operations | 3 | 4 | 12 | High
TR-19 | ADCS lacks sufficient torque to de-tumble the combined spacecraft+target body within a 30-minute window (can change the time interval just randomish realistic time set) | 3 | 4 | 12 | High
TR-20 | Star tracker blinding by the Sun, Moon or Earth during an eclipse transition causes loss of attitude knowledge | 3 | 3 | 9 | Medium
TR-21 | Thruster Exhaust Contact: Hot exhaust gases emitted during proximity operations melt or structurally weaken target surfaces, leading to fragmentation or unpredictable attitude dynamics that prevent successful capture. | 2 | 4 | 8 | Medium
TR-22 | Timeline extension: Additional approach attempts, or corrections, may significantly extend the overall mission duration and resource use | 2 | 3 | 6 | Medium
TR-23 | On-board storage structure for extracted components fails under repeated GEO thermal cycling (-180 to +150 °C) RANGE OF TEMPREATURES GOD DID | 2 | 4 | 8 | Medium
TR-24 | GNC mode transition failure (transfer→RPO→capture→departure) leaves spacecraft in undefined state | 2 | 4 | 8 | Medium
TR-25 | Launch vehicle anomaly or delay results in loss of spacecraft or failure to reach target GEO orbit | 1 | 5 | 5 | Medium
TR-26 | Unknown or unexpected centre-of-mass offset in captured debris causes uncontrolled attitude divergence of the combined system during transport | 3 | 4 | 12 | High
TR-27 | Recycling hub loses station-keeping capability and drifts from its operational position, preventing tug rendezvous and debris handover | 2 | 4 | 8 | Medium
TR-28 | Docking mechanism fails during tug return to recycling hub with debris attached, preventing debris handover and blocking subsequent capture cycles | 2 | 4 | 8 | Medium
TR-29 | Structural fragmentation of target spacecraft during capture due to undetected material fatigue or microcracking, generating secondary debris | 2 | 5 | 10 | High
TR-30 | Ground mission operations centre failure causes extended loss of spacecraft commanding and telemetry monitoring during an active operational phase | 2 | 4 | 8 | Medium

## Pre-Mitigation Map
Pre-Mitigation Risk Map — REAVER DSE
L \ C | C1 | C2 | C3 | C4 | C5
L5 |  |  | R-04
L4 |  |  |  | R-01 R-02
L3 |  |  | R-05 R-09 | R-03 R-06 R-10 | R-07
L2 |  |  |  | R-08
L1
← Consequence (C) →
Legend: | Low (1–4) | Medium (5–9) | High (10–16) | Critical (20–25)

## Post-Mitigation Map
Post-Mitigation Risk Map — REAVER DSE
L \ C | C1 | C2 | C3 | C4 | C5
L5
L4
L3 |  |  | R-04
L2 |  |  | R-01 R-02 R-05 R-08 R-09 | R-03 R-06 R-10 | R-07
L1
← Consequence (C) →
Legend: | Low (1–4) | Medium (5–9) | High (10–16) | Critical (20–25)